## Schedule and Milestones
Week
Task | Description | Assignment | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Track Straight Line | All | bar: Week 2
1.1 | PID Controller implementation | Erik | bar: Week 2
1.1a | Look over previous teams controllers | Erik | bar: Week 2
1.1b | Borrow and improve on controller | Erik | bar: Week 2
1.2 | Line Sensor Calibration | Erik | bar: Week 2
1.2a | Look over previous teams code for sensor | Erik | bar: Week 2
1.2b | Borrow and improve on sensor | Erik | bar: Week 2
2 | Track a Curved Line | Erik | bar: Week 3
2.1 | Further line sensor calibration | Erik | bar: Week 3
2.2 | Development and testing | Erik | bar: Week 3
3 | Networking | Wesley | bar: Week 3 to Week 4
3.1 | Look over previous teams code for networking | Wesley | bar: Week 3 to Week 4
3.2 | Borrow and improve on code | Wesley | bar: Week 3 to Week 4
4 | Mapping and Tracking | bar: Week 5 to Week 6
4.1 | Maze solving algorithm | bar: Week 5 to Week 6
4.1a | 2D Array to map where the mice are | Wesley | bar: Week 5 to Week 6
4.2 | Transmit the solution to other mouse | Wesley | bar: Week 5 to Week 6
5 | Team Motion | bar: Week 7 to Week 8
5.1 | Code for all three mice moving at once to map maze | bar: Week 7 to Week 8
5.2 | Testing and development | bar: Week 7 to Week 8
6 | Coordinated Activity | bar: Week 9 to Week 10
6.1 | Code for all three mice solving the maze together | bar: Week 9 to Week 10
6.2 | Testing and development | bar: Week 9 to Week 10
7 | Custom Challenge | bar: Week 11 to Week 13
7.1 | Determine challenge | bar: Week 11 to Week 13
7.2 | Code for the challenge | bar: Week 11 to Week 13
7.3 | Testing and development | bar: Week 11 to Week 13
8 | Class Challenge | bar: Week 14 to Week 15
8.1 | Final Tests and development | bar: Week 14 to Week 15
9 | Final Report | bar: Week 16